## Phase_Gantt
Project: | STM32WL Sensor Board – LoRa + ADC System
Engineer: | Caoilte Donohoe
Version: | Phase Gantt v1.5
Last Updated: | 2025-09-20
Project Link: | https://github.com/CDonohoe-Designs/STM32WL-LoRa-Sensor-Board-Portfolio
EVT/PVT/DVT Phase Gantt
Phase | Task | Duration (days) | % Complete | Start | Finish | Completed Days | In Progress Days | Planned Days
EVT | Research & Simulation (LTspice + Python) | 10 | 100 | 2025-08-29 | 2025-09-08 | 10 |  | 0
EVT | Schematic (Altium) | 7 | 100 | 2025-09-09 | 2025-09-16 | 7 |  | 0
EVT | PCB Layout (Altium) | 10 | 100 | 2025-09-17 | 2025-09-27 | 10 |  | 0
EVT | Layout Rev A (Done) | 5 | 100 | 2025-09-28 | 2025-09-20 | 5 |  | 0
EVT | Gerbers Released (Milestone) | 2 | 50 | 2025-09-21 | 2025-09-23 | 0 | 1 | 0
EVT | EVT#1 Fab & Assembly | 14 | 0 | 2025-09-24 | 2025-10-08 | 0 |  | 14
EVT | Bring-up (Power, MCU, AFE) | 7 | 0 | 2025-10-09 | 2025-10-16 | 0 |  | 7
EVT | EVT Complete (Milestone) | 0 | 0 | 2025-10-17 | 2025-10-17 | 0 |  | 0
DVT | Rev B Freeze | 5 | 0 | 2025-10-18 | 2025-10-23 | 0 |  | 5
DVT | DVT#1 Build | 14 | 0 | 2025-10-24 | 2025-11-07 | 0 |  | 14
DVT | EMC Pre-Scan | 5 | 0 | 2025-11-08 | 2025-11-13 | 0 |  | 5
DVT | Test Fixture Design | 10 | 0 | 2025-11-14 | 2025-11-24 | 0 |  | 10
DVT | DVT Complete (Milestone) | 0 | 0 | 2025-11-25 | 2025-11-25 | 0 |  | 0
PVT | Pilot Build (50 units) | 14 | 0 | 2025-11-26 | 2025-12-10 | 0 |  | 14
PVT | Formal Compliance CE/FCC/ETSI | 10 | 0 | 2025-12-11 | 2025-12-21 | 0 |  | 10
PVT | Fixture Validation in Factory | 5 | 0 | 2025-12-22 | 2025-12-27 | 0 |  | 5
PVT | PVT Complete (Milestone) | 0 | 0 | 2025-12-28 | 2025-12-28 | 0 |  | 0
Launch | GA Release | 0 | 0 | 2025-12-29 | 2025-12-29 | 0 |  | 0
EVT/DVT/PVT Phase Gantt ---Details
Phase | Details
Project: | STM32WL Sensor Board – LoRa + ADC System
Engineer: | Caoilte Donohoe
Version: | Phase Gantt v1.5
Last Updated: | 2025-09-20
Project Link: | https://github.com/CDonohoe-Designs/STM32WL-LoRa-Sensor-Board-Portfolio
EVT (Engineering Validation Test) Purpose: Prove the design concept works electrically and functionally.
Research & Simulation (LTspice + Python)
Schematic (Altium)
PCB Layout (Altium)
Layout Rev A (Done)
Gerbers Released (Milestone, 50% In Progress)
EVT#1 Fab & Assembly
Bring-up (Power, MCU, AFE)
EVT Complete (Milestone)
DVT (Design Validation Test): Purpose: Design refinement — post-EVT fixes, compliance prep, and manufacturability.
Rev B Freeze
DVT#1 Build
EMC Pre-Scan
Test Fixture Design
DVT Complete (Milestone)
PVT (Production Validation Test):Purpose: Prove manufacturability at scale and ensure compliance before launch.
Pilot Build (50 units)
Formal Compliance CE/FCC/ETSI
Fixture Validation in Factory
PVT Complete (Milestone)
Launch:Purpose: Market release milestone.
GA Release (General Availability)

## Design Phase Details
EVT/PVT/DVT Phase Gantt ---Details
Phase | Details
Project: | STM32WL Sensor Board – LoRa + ADC System
Engineer: | Caoilte Donohoe
Version: | Phase Gantt v1.5
Last Updated: | 2025-09-20
Project Link: | https://github.com/CDonohoe-Designs/STM32WL-Sensor-Board-Report
EVT (Engineering Validation Test)
Research & Simulation (LTspice + Python)
Schematic (Altium)
PCB Layout (Altium)
Layout Rev A (Done)
Gerbers Released (Milestone, 50% In Progress)
EVT#1 Fab & Assembly
Bring-up (Power, MCU, AFE)
EVT Complete (Milestone)
Purpose: Prove the design concept works electrically and functionally.
DVT (Design Validation Test)
Rev B Freeze
DVT#1 Build
EMC Pre-Scan
Test Fixture Design
DVT Complete (Milestone)
Purpose: Design refinement — post-EVT fixes, compliance prep, and manufacturability.
PVT (Production Validation Test)
Pilot Build (50 units)
Formal Compliance CE/FCC/ETSI
Fixture Validation in Factory
PVT Complete (Milestone)
Purpose: Prove manufacturability at scale and ensure compliance before launch.
Launch
GA Release (General Availability)
Purpose: Market release milestone.